## Dashboard
Jean-Marc Planning Rénovation |  | d-avr-yy to d-mars-yy
Topic | Task | Acteur | Start Date | End Date | Duration | Days comp. | Progress | Budget | Actual | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07
Gros-œuvre | Adaptation Porte d'entrée | Ets Construction | 2021-09-03 | 2021-09-03 | 1 | 0 | 0% | 1590 | 0
| Remplacement linteaux en bois | Ets Construction | 2021-09-03 | 2021-09-03 | 1 | 0 | 0% | 1431 | 0
| Escaliers | Ets Construction | 2021-09-06 | 2021-09-07 | 2 | 0 | 0% | 2438 | 0
| Démolition cheminée | Ets Construction | 2021-09-03 | 2021-09-03 | 1 | 0 | 0% | 2544 | 0
| Colonne en béton pour baie vitrée | Ets Construction | 2021-08-31 | 2021-08-31 | 1 | 0 | 0% | 4664 | 0
| Ouverture fenêtres | Ets Construction | 2021-08-30 | 2021-08-31 | 2 | 1 | 50% | 5088 | 0
Menuiserie extétieure | Montage | Arnaud Pierret | 2021-09-15 | 2021-09-16 | 2 | 0 | 0% | 19398 | 7759.2
Façade Côté Sud | Montage échaffaudage | Bertrand Hiernaux | 2021-10-04 | 2021-10-04 | 1 | 0 | 0% | 0 | 0
| Démontage Eternit | Bertrand Hiernaux | 2021-10-05 | 2021-10-05 | 1 | 0 | 0% | 0 | 0
| Isolation et nouveau bardage | Bertrand Hiernaux | 2021-10-06 | 2021-10-12 | 5 | 0 | 0% | 12205 | 0
| Démontage échaffaudage | Bertrand Hiernaux | 2021-10-13 | 2021-10-13 | 1 | 0 | 0% | 0 | 0
Toiture | Démontage toiture existante | Alain Invernizzi | 2021-10-01 | 2021-10-05 | 3 | 0 | 0% | 0 | 0
| Travaux de charpente | Alain Invernizzi | 2021-10-08 | 2021-10-11 | 2 | 0 | 0% | 0 | 0
| Pause des vélux | Alain Invernizzi | 2021-10-12 | 2021-10-13 | 2 | 0 | 0% | 0 | 0
| Revêtement toiture | Alain Invernizzi | 2021-10-14 | 2021-10-22 | 7 | 0 | 0% | 32765 | 0
| Isolation Toiture | Samuel Schmit | 2021-10-23 | 2021-10-27 | 3 | 0 | 0% | 6212 | 0
| Pose des panneaux photovoltaïques | Alter Energie | 2021-10-22 | 2021-10-22 | 1 | 0 | 0% | 5745.19 | 1149.03
Sanitaire | Conduites froid et chaud et évacuation | Alter Energie | 2021-09-23 | 2021-09-30 | 6 | 5 | 83.33% | 7177.26 | 0
| installation adoucisseur d'eau | Bayard | 2021-12-20 | 2021-12-20 | 1 | 0 | 0% | 1535.94 | 0
Electricite | Cablâge initial et mise en terre | Christophe Braconnier | 2021-04-23 | 2021-04-23 | 1 | 1 | 100% | 3215 | 3215.2
| Carotages (21x) | Christophe Braconnier | 2021-05-21 | 2021-05-21 | 1 | 1 | 100% | 525 | 0
| Cablâge suite + réseau partie | Christophe Braconnier | 2021-09-27 | 2021-10-25 | 21 | 0 | 0% | 3884 | 0
| Installation des tableaux et divers appareillages | Christophe Braconnier | 2021-10-02 | 2022-03-17 | 119 | 0 | 0% | 10148 | 0
| Déplacement du compteur électrique | Ores | 2021-11-02 | 2021-11-02 | 1 | 0 | 0% | 854.6 | 0
VMC | Installation conduite et appareillage | Samuel Schmit | 2021-10-25 | 2021-10-28 | 4 | 0 | 0% | 14966 | 5104.92
| Mise en route | Samuel Schmit | 2021-11-08 | 2021-11-08 | 1 | 0 | 0% | 0 | 0
Sols | Isolation | Samuel Schmit | 2021-11-09 | 2021-11-09 | 1 | 0 | 0% | 6226 | 0
| Chappe | Samuel Schmit | 2021-11-10 | 2021-11-11 | 2 | 0 | 0% | 4667 | 0
| Séchage chappe | Samuel Schmit | 2021-11-12 | 2021-12-10 | 21 | 0 | 0% | 0 | 0
| Pose du parquet | Samuel Schmit | 2022-01-27 | 2022-02-02 | 5 | 0 | 0% | 19988.28 | 0
| Chappe sur marches d'escalier | Samuel Schmit | 2022-02-03 | 2022-03-03 | 21 | 0 | 0% | 647 | 0
| Carrelage sur marches | Samuel Schmit | 2022-03-04 | 2022-03-04 | 1 | 0 | 0% | 0 | 0
Murs | Isolation des murs intérieurs | Samuel Schmit | 2021-11-17 | 2021-11-19 | 3 | 0 | 0% | 13343.28 | 0
| Enduits et peintures | Myself | 2022-02-05 | 2022-03-07 | 21 | 0 | 0% | 0 | 0
| Travaux de sablage du mur apparent | A.L Façade | 2021-12-01 | 2021-12-07 | 5 | 0 | 0% | 2989 | 0
Chauffage | inst chaudière et protocole mise en chauffe | Alter Energie | 2021-12-11 | 2021-12-20 | 6 | 0 | 0% | 31998 | 4800
Plâtres | Travaux de plâtrage cloisons et murs porteurs | Jean-Marc | 2021-12-21 | 2022-01-27 | 28 | 0 | 0% | 0 | 0
Menuiserie intérieure | commande escalier et portes , délais | Menuiserie Poncin | 2022-01-03 | 2022-02-15 | 32 | 0 | 0% | 0 | 0
| Pause escalier en bois | Menuiserie Poncin | 2022-02-03 | 2022-02-03 | 1 | 0 | 0% | 0 | 0
| Portes intérieures | Menuiserie Poncin | 2022-03-08 | 2022-03-10 | 3 | 0 | 0% | 0 | 0
| Mobilier sur mesure | Menuiserie Poncin | 2022-03-11 | 2022-03-14 | 2 | 0 | 0% | 0 | 0
| Garde-corp mezzanine | Siroco | 2022-02-03 | 2022-02-03 | 1 | 0 | 0% | 2805 | 0
Salle de bain | Carrelages au mur, douche et finitions | Samuel Schmit | 2022-01-27 | 2022-01-28 | 2 | 0 | 0% | 4641 | 0
| Mobilier de sdb et installation | Samuel Schmit | 2022-02-04 | 2022-02-04 | 1 | 0 | 0% | 9013.82 | 9013.82
Cuisine | Montage cuisine | Interni | 2022-02-03 | 2022-02-03 | 1 | 0 | 0% | 28800 | 8540
Déménagement | Nettoyage | Myself | 2022-03-15 | 2022-03-23 | 7 | 0 | 0% | 0 | 0
| Déménagement | Myself | 2022-03-23 | 2022-03-29 | 5 | 0 | 0% | 0 | 0
Aménagement intérieur | Pose des tablettes de fenêtre | Samuel Schmit | 2022-02-05 | 2022-02-08 | 2 | 0 | 0% | 0 | 0
Total général | [7 empty] | 261504.37 | 39582.17
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
Cette forme représente un segment. Les segments sont pris en charge dans Excel 2010 ou version ultérieure. En revanche, si la forme a été modifiée dans une version précédente d’Excel, ou si le classeur a été enregistré dans Excel 2003 ou une version précédente, vous ne pouvez pas utiliser le segment.
2%

## Workings
Budget v Actual Doughnut & Bar Chart |  |  | Tasks Bar Chart |  |  | Overall Progress - Days Completed v Duration Doughnut Chart |  |  |  |  | Scroll bar position
| Actual | Budget | Not Started | 42 | =NB.SI(Dashboard!H6:H51;"="&0) | Values |  | Doughnut Chart | % | Formula | 128
Bar Chart | 39582.17 | 261504.37 | In Progress | 2 | =NB.SI.ENS(Dashboard!H6:H51;"<>"&0;Dashboard!H6:H51;"<"&1) | Days completed | 8 | Days Completed | 2.21% | =J3/$J$4
Dougnut Chart | 15.14% | 84.86% | Completed | 2 | =NB.SI(Dashboard!H6:H51;"="&1) | Duration | 362 | Days Remaining | 97.79% | =1-M3
|  | =1-B4 | Remaining | 44 | =F3+F2
|  |  | Total Tasks | 45 | =NBVAL(Dashboard!B6:B50)

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
Gros-œuvre | Adaptation Porte d'entrée | Ets Construction | 2021-09-03 | 1 | 2021-09-03 | 0 | 0% | 1590 | 0
Gros-œuvre | Remplacement linteaux en bois | Ets Construction | 2021-09-03 | 1 | 2021-09-03 | 0 | 0% | 1431 | 0
Gros-œuvre | Escaliers | Ets Construction | 2021-09-06 | 2 | 2021-09-07 | 0 | 0% | 2438 | 0
Gros-œuvre | Démolition cheminée | Ets Construction | 2021-09-03 | 1 | 2021-09-03 | 0 | 0% | 2544 | 0
Gros-œuvre | Colonne en béton pour baie vitrée | Ets Construction | 2021-08-31 | 1 | 2021-08-31 | 0 | 0% | 4664 | 0
Gros-œuvre | Ouverture fenêtres | Ets Construction | 2021-08-30 | 2 | 2021-08-31 | 1 | 50% | 5088 | 0
Menuiserie extétieure | Montage | Arnaud Pierret | 2021-09-15 | 2 | 2021-09-16 | 0 | 0% | 19398 | 7759.2
Façade Côté Sud | Montage échaffaudage | Bertrand Hiernaux | 2021-10-04 | 1 | 2021-10-04 | 0 | 0% | 0 | 0
Façade Côté Sud | Démontage Eternit | Bertrand Hiernaux | 2021-10-05 | 1 | 2021-10-05 | 0 | 0% | 0 | 0
Façade Côté Sud | Isolation et nouveau bardage | Bertrand Hiernaux | 2021-10-06 | 5 | 2021-10-12 | 0 | 0% | 12205 | 0
Façade Côté Sud | Démontage échaffaudage | Bertrand Hiernaux | 2021-10-13 | 1 | 2021-10-13 | 0 | 0% | 0 | 0
Toiture | Démontage toiture existante | Alain Invernizzi | 2021-10-01 | 3 | 2021-10-05 | 0 | 0% | 0 | 0
Toiture | Travaux de charpente | Alain Invernizzi | 2021-10-08 | 2 | 2021-10-11 | 0 | 0% | 0 | 0
Toiture | Pause des vélux | Alain Invernizzi | 2021-10-12 | 2 | 2021-10-13 | 0 | 0% | 0 | 0
Toiture | Revêtement toiture | Alain Invernizzi | 2021-10-14 | 7 | 2021-10-22 | 0 | 0% | 32765 | 0
Toiture | Pose des panneaux photovoltaïques | Alter Energie | 2021-10-22 | 1 | 2021-10-22 | 0 | 0% | 5745.19 | 1149.03
Toiture | Isolation Toiture | Samuel Schmit | 2021-10-23 | 3 | 2021-10-27 | 0 | 0% | 6212 | 0
Sanitaire | Conduites froid et chaud et évacuation | Alter Energie | 2021-09-23 | 6 | 2021-09-30 | 5 | 83.33% | 7177.26 | 0
Electricite | Cablâge initial et mise en terre | Christophe Braconnier | 2021-04-23 | 1 | 2021-04-23 | 1 | 100% | 3215 | 3215.2
Electricite | Carotages (21x) | Christophe Braconnier | 2021-05-21 | 1 | 2021-05-21 | 1 | 100% | 525 | 0
Electricite | Cablâge suite + réseau partie | Christophe Braconnier | 2021-09-27 | 21 | 2021-10-25 | 0 | 0% | 3884 | 0
Electricite | Installation des tableaux et divers appareillages | Christophe Braconnier | 2021-10-02 | 119 | 2022-03-17 | 0 | 0% | 10148 | 0
Electricite | Déplacement du compteur électrique | Ores | 2021-11-02 | 1 | 2021-11-02 | 0 | 0% | 854.6 | 0
VMC | Installation conduite et appareillage | Samuel Schmit | 2021-10-25 | 4 | 2021-10-28 | 0 | 0% | 14966 | 5104.92
VMC | Mise en route | Samuel Schmit | 2021-11-08 | 1 | 2021-11-08 | 0 | 0% | 0 | 0
Sols | Isolation | Samuel Schmit | 2021-11-09 | 1 | 2021-11-09 | 0 | 0% | 6226 | 0
Sols | Chappe | Samuel Schmit | 2021-11-10 | 2 | 2021-11-11 | 0 | 0% | 4667 | 0
Sols | Séchage chappe | Samuel Schmit | 2021-11-12 | 21 | 2021-12-10 | 0 | 0% | 0 | 0
Murs | Isolation des murs intérieurs | Samuel Schmit | 2021-11-17 | 3 | 2021-11-19 | 0 | 0% | 13343.28 | 0
Murs | Travaux de sablage du mur apparent | A.L Façade | 2021-12-01 | 5 | 2021-12-07 | 0 | 0% | 2989 | 0
Chauffage | inst chaudière et protocole mise en chauffe | Alter Energie | 2021-12-11 | 6 | 2021-12-20 | 0 | 0% | 31998 | 4800
Sanitaire | installation adoucisseur d'eau | Bayard | 2021-12-20 | 1 | 2021-12-20 | 0 | 0% | 1535.94 | 0
Plâtres | Travaux de plâtrage cloisons et murs porteurs | Jean-Marc | 2021-12-21 | 28 | 2022-01-27 | 0 | 0% | 0 | 0
Menuiserie intérieure | commande escalier et portes , délais | Menuiserie Poncin | 2022-01-03 | 32 | 2022-02-15 | 0 | 0% | 0 | 0
Sols | Pose du parquet | Samuel Schmit | 2022-01-27 | 5 | 2022-02-02 | 0 | 0% | 19988.28 | 0
Aménagement intérieur | Pose des tablettes de fenêtre | Samuel Schmit | 2022-02-05 | 2 | 2022-02-08 | 0 | 0% | 0 | 0
Sols | Chappe sur marches d'escalier | Samuel Schmit | 2022-02-03 | 21 | 2022-03-03 | 0 | 0% | 647 | 0
Menuiserie intérieure | Pause escalier en bois | Menuiserie Poncin | 2022-02-03 | 1 | 2022-02-03 | 0 | 0% | 0 | 0
Sols | Carrelage sur marches | Samuel Schmit | 2022-03-04 | 1 | 2022-03-04 | 0 | 0% | 0 | 0
Salle de bain | Carrelages au mur, douche et finitions | Samuel Schmit | 2022-01-27 | 2 | 2022-01-28 | 0 | 0% | 4641 | 0
Salle de bain | Mobilier de sdb et installation | Samuel Schmit | 2022-02-04 | 1 | 2022-02-04 | 0 | 0% | 9013.82 | 9013.82
Murs | Enduits et peintures | Myself | 2022-02-05 | 21 | 2022-03-07 | 0 | 0% | 0 | 0
Cuisine | Montage cuisine | Interni | 2022-02-03 | 1 | 2022-02-03 | 0 | 0% | 28800 | 8540
Menuiserie intérieure | Portes intérieures | Menuiserie Poncin | 2022-03-08 | 3 | 2022-03-10 | 0 | 0% | 0 | 0
Menuiserie intérieure | Mobilier sur mesure | Menuiserie Poncin | 2022-03-11 | 2 | 2022-03-14 | 0 | 0% | 0 | 0
Menuiserie intérieure | Garde-corp mezzanine | Siroco | 2022-02-03 | 1 | 2022-02-03 | 0 | 0% | 2805 | 0
Déménagement | Nettoyage | Myself | 2022-03-15 | 7 | 2022-03-23 | 0 | 0% | 0 | 0
Déménagement | Déménagement | Myself | 2022-03-23 | 5 | 2022-03-29 | 0 | 0% | 0 | 0
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)

## Instructions
Project Management Dashboard Instructions
Step 1 | Format source data in an Excel Table - CTRL+T
Step 2 | Dashboard PivotTable
2.01 | Insert Dashboard PivotTable in cell A5
2.02 | Format PivotTable with Tabular layout & no subtotals
2.03 | Format PivotTable Budget & Actual values via Field Settings
2.04 | PivotTable Options > Turn off Expand/Collapse buttons
2.05 | Format PivotTable in light grey
Step 3 | Insert Table for Tasks Bar Chart on Workings Sheet
Bar chart height 3.73 x 9.0 wide.
Step 4 | Insert doughnut chart PivotTable for Overall Completed - Completed Days vs Duration
Chart height 3.73 x width 3.25
Step 5 | Insert budget vs actual doughnut & bar chart PivotTable on Workings Sheet
Doughnut hole 58%
Bar chart series overlap -30%, gap width 0%
Doughnut chart height 3.73 x width 3.25, Bar Chart height 3.73 x width 6.
Step 6 | Insert Slicers for Project and Manager fields & connect to all PivotTables
Step 7 | Add text for date range to header cell F1:
=TEXT(MIN(D6:D51),"d-mmm-yy")&" to "&TEXT(MAX(E6:E51),"d-mmm-yy")
Step 8 | Add scroll bar and link to a cell P2 in the Workings sheet
Step 9 | Add calendar dates in cell K5:AJ5
Note: the formula below only works in Excel for Office 365.
=SEQUENCE(1,26,MIN(Table1[Start Date])+Workings!P2,1)
Step 10 | Gantt Chart - Conditional Formatting (extend the 'applies to' range to allow for growth in your data)
10.1 | Add data bars to Progress column of PivotTable
10.2 | Format Dates in row 5
10.3 | Shade columns for weekend dates
10.4 | Add fill colour for completed dates
10.5 | Add fill colour for in progress dates
10.6 | Add cell borders for 'not started' dates
10.7 | Add grey shading to Grand Total row
Step 11 | Freeze Panes at cell A6
CLICK TO WATCH THE
VIDEO TUTORIAL

## More Resources
More Resources
Courses
| Excel Dashboard Course | https://www.myonlinetraininghub.com/excel-dashboard-course
| Power Query Course | https://www.myonlinetraininghub.com/excel-power-query-course
| Power Pivot Course | https://www.myonlinetraininghub.com/power-pivot-course
| Power BI Course | https://www.myonlinetraininghub.com/power-bi-course
Tutorials
| Custom Number Formats | https://www.myonlinetraininghub.com/excel-custom-number-format-guide
| WORKDAY.INTL Function | https://www.myonlinetraininghub.com/excel-functions/excel-workday-intl-function
| WEEKDAY Function | https://www.myonlinetraininghub.com/excel-functions/excel-weekday-function
| SEQUENCE Function | https://www.myonlinetraininghub.com/excel-sequence-function
| Conditional Formatting Gantt | https://www.myonlinetraininghub.com/excel-conditional-formatting-gantt-chart
| Conditional Formatting Formulas | https://www.myonlinetraininghub.com/excel-conditional-formatting-with-formulas
| TEXT Function | https://www.myonlinetraininghub.com/excel-text-function
Excel Support
| Excel Forum | https://www.myonlinetraininghub.com/excel-forum
| Contact | website@myonlinetraininghub.com

## Dashboard Protection
Protecting your dashboard
2. Worksheet Protection - You'll find the Worksheet Protection on the Review tab:
1. Slicers - prevent users activating the pull handles when using the Slicer by selecting 'Disable resizing and moving' in the Slicer Position and Layout setting (right-click Slicer).
Or Slicers - Simply protect the worksheet containing the Dashboard, but make sure you 'unprotect' Slicers so that they can still be clicked:
Before Disabling Resizing
After Disabling Resizing
If your Dashboard sheet contains a PivotTable, make sure 'Use PivotTable & PivotChart' is checked so that Slicers work.
Note, this will prevent the PivotTables in the entire file from being refreshed, so if you're planning on updating your dashboard with new data, then option 3 is preferred.
4. Protect Workbook
Once you've 'VeryHidden' the sheets containing your workings and data you need to protect your workbook so your users can't unhide them.
WARNING: this protection is not bullet proof. If a user wants to get to your underlying data they can find a way. A Google search will reveal various ways to crack your password, or simply remove the protection.
Therefore Worksheet Protection should be used to prevent users breaking your report, but don't count on it protecting super sensitive information.
3. Hide Worksheets
A better solution is to set the property for the
sheets containing your data and workings to
VeryHidden in the VB Editor Alt+F11.
When you right-click the sheet tab there is no
indication that worksheets are hidden when
their properties are set to 'xlSheetVeryHidden'